## Details
Date (DD-MM-YY) |  | Customer | PM | Type | Resource |  | VPN |  |  | Status |  | Hours Spent |  | Comments | Tickets
Testing | Orientation |  |  |  | Testing | Orientation | App/IP | User | Pass | Testing | Orientation | Testing | Orientation
2025-11-14 | 2025-11-25 | Syscom Taiwan | Shobhna | VPN | Jabali | Jabali | Global Protect 60.251.169.194 | exthpe_jabali_searcot_karanam | YGbux#V3mrip | Done | Done | 6 | 2 | Local S3 issue. Fixed | 5393542826
2026-03-06 | 2026-03-12 | Verizon | Shobhna | VPN | Jabali | Jabali | Forticlient https://63.97.174.133:10443/ 10443 | asingh | Xwa8xMWFcRjY3V0H | Done | Done | 3 | 2 | Need to add to host file 10.77.25.22 home.rcn-pcai-ai-application.msdctf.local 10.77.25.22 *.rcn-pcai-ai-application.msdctf.local 10.77.25.22 keycloak.rcn-pcai-ai-application.msdctf.local 10.77.25.22 token-service.rcn-pcai-ai-application.msdctf.local 10.77.25.22 kubeflow.rcn-pcai-ai-application.msdctf.local 10.77.25.22 oauth2-proxy.rcn-pcai-ai-application.msdctf.local 10.77.25.22 welcome.rcn-pcai-ai-application.msdctf.local/
2026-03-12 | 2026-06-13 | Largan | Li, Jiuxu | Screen Share | Jabali | Jabali | NA | NA | NA | Done | Done | 5 | 2 |  | 5401716615
|  | Tu Site Network |  |  | Jabali |  |  |  |  | Done
2026-02-02 |  | Fundación Médica de Mar del Plata | Shobhna | Screen Share | Suraj | Jabali | NA | NA |  | Done |  | 3
|  | Bridgetak |  |  | DJ |  |  |  |  | Done |  | 3 | 2
|  | Quanser |  |  | DJ |  |  |  |  | Done |  | 3 | 2
|  | Unisys |  |  | Ashish |  |  |  |  | Done
|  | Hitachi |  |  | Ashish |  |  |  |  | Done
2026-10-02 |  | Peraton |  | Screen Share | Sanjana |  |  |  |  | Done |  | 2 | 1
2026-06-03 |  | TrueMove | Shobna | Screen Share | Sanjana | DJ |  |  |  | Done |  | 4 | 2 | PCAI had URLs blocked which had to be whitelisted
|  | Dallas Cowboys |  |  | Ashish |  |  |  |  | Done
|  | 2 Degrees |  |  | DJ | DJ |  |  |  | Done |  |  | 2
2026-12-02 |  | Court of Justice | Lopamudra Dash | Screen Share | Suraj |  | NA | NA |  | Done |  | 2
2026-02-24 |  | Kaczmarski |  | VPN | Pransshu | Jabali |  |  |  | Done | Done |  | 2
2026-05-03 |  | HPE-GIT-2nd-G2-Large-EXP-COLO1 | Aisiri/Praveen | VPN | Suraj | DJ | NA | NA |  | Done |  | 3 | 2
2026-02-03 |  | Danfoss G2 Large | Debaroon | VPN | Suraj |  | u449364@danfoss.com | jabali-searcot.karanam@hpe.com | N@@Dar!dr@m.1123 | Done |  | 2.5
2026-06-03 |  | Unisystem Upgrade | Shobhna | Screen Share | Suraj |  | NA | NA |  | Done |  | 2
2026-02-03 |  | Kaczmarski Upgrade | Shobhna | VPN | Pransshu |  |  |  |  | Done
2026-06-03 |  | Sunway Digital | Lopamudra Dash | VPN | Pransshu | DJ |  |  |  | Done
2026-05-03 |  | HPE-GIT-G2-Large-EXP-COLO2 | Aarti | VPN | Pransshu | DJ |  |  |  | Done |  |  | 3
2026-11-03 |  | COFORGE | Praveen | Screen Share | Pransshu |  |  |  |  | Done
2026-12-03 | 2026-03-31 | ZAMEK KRÓLEWSKI NA WAWELU (The Royal Castle on Wawel Hill) | Hemanth | Screen Share | Sanjana | Jabali |  |  |  | Done | Done | 2 | 1
2026-03-15 |  | Sunway Digital Upgrade | Lopamudra Dash | VPN | Pransshu | Jabali |  |  |  | Done | Done |  | 1
2026-03-16 |  | Court of Justice Upgrade | Lopamudra Dash | Screen Share | Pransshu | DJ |  |  |  | Done
2026-03-18 |  | Quanser Upgrade | Debaroon | VPN | Suraj | DJ | Forticlient mkvpn.quanser.com | Ashukla | Quan#@!@^ | Done |  | 3
2026-03-20 |  | Peraton Upgrade | Kashif | Screen Share | Pransshu | DJ |  |  |  | Done
2026-03-24 | 2026-04-07 | Columbia Lafayette | Hemanth | Screen Share | Sanjana | DJ |  |  |  | Done |  | 4 | 2 | PCAI had URLs blocked which had to be whitelisted Notebook Kernel was disconnected and Ingress pod had to be restarted
2026-03-27 | 2026-04-07 | Fraunhofer Gesellschaft | Praveen | Screen Share | Suraj | Jabali | NA | NA | NA | Done | Done | 1 | 2
2026-04-07 |  | COLO1-GIT-PCAIG2-LG8N-2 | Aisiri | VPN | Suraj | DJ | HPE Network |  |  | Done |  | 2.5
2026-04-14 |  | Two Degrees Mobile Limited - Upgrade | Aarti | VPN | Suraj |  | thirdparty.2degrees.nz | nzc\Vikas.Sharma2 | Vikasvishalgian$22ji | Done |  | 3 | 1 | Data Sources as OPA Server wasn’t Scaled Properly | 5402322925
2026-04-13 |  | TrueMove Upgrade | Shobhna | VPN | Pransshu | DJ |  |  |  | Done
2026-04-13 | 2026-04-20 | Lupin Ltd | Debaroon | VPN | Suraj | Jabali | https://isecure.lupin.com/Home/Login | "+919901378424" | Authenticator Code | Done | Done | 2.5 | 1 | Slow Network, Model Deployment Consumed time
2026-04-14 |  | Comcast | Praveen | Screen Share | Pransshu | DJ
2026-04-07 | 2026-04-22 | PCAI G2 CTO - L-INFRAESTRUTURAS DE PORTUGAL, S.A. | Lopamudra Dash | VPN | Sanjana | Jabali | https://urldefense.com/v3/__https://vpn.infraestruturasdeportugal.pt/sslvpn/Login/Login__;!!NpxR!jweiTjtYHp71a0luU2zmAIOIiUiy3kv7n_DbXVzoqpwPZep10EQn6rsNWH1TooMX3uBrQYgbYyUdzQRBh3jXnh_eH2C2gp5Yo4M$ https://firewall.refer.pt/PortalMain | s.upadhyaya.pcai@mgmt.local | PRvi,78#49! | Done |  | 15 | 1 | 1. python https://pypi.org had to be whitelisted on production network 2. https://github.com/HPEEzmeral had to be whitelisted on production network 3. firewall rules had to be modified twice to resolve DNS related issue that was causing github to have no access on production network, thereby leading to failure to download DAGs on Airflow. 4. Kernel got disconnected leading to failures to run notebooks | 5402228222
|  | Louieville | Kashif | Screen Share | DJ | DJ | [5 empty] | 6 | 2
2026-04-23 |  | SGMAI Interna Unit 2 | Kashif | VPN | Suraj | DJ | mobilidade.rnsi.mai.gov.pt | hpe_suraj.r-s-ext | (AEG<F3z | Done |  | 2.5 |  | Slow Network, Notebook Server spinning issue | 5402495733
2026-04-20 | NA | ENI SPA | Yousuff Shariff | VPN | Sanjana | DJ |  |  |  | Done |  | 2 | 1
2026-04-24 |  | Jar Electrónica Aplicada PCAI | Aarti | Screen Share |  | DJ | NA | NA | NA | Done |  | 2
2026-04-29 |  | Jabartan | Shobhna | Screen Share | Pransshu |  | NA | NA | NA | Done |  |  |  | URL Blacklisted
2026-05-06 |  | Infomina | Tom Sunder | VPN | Sanjana |  | vpn.cloud.infomina.ai:10444 | Username: hpe-installer Password: ponzec-kUwsup-nyxze0 |  | Done |  | 1 | 1.5
2026-05-12 |  | Tatung Systems | Tom Sunder | Screen Share | Pransshu |  | NA | NA | NA | Done |  |  |  | 4th pipeline done in calling_llm not openai
2026-05-14 |  | Equinix Columbia | Hemanth | Screen Share | Pransshu |  | NA | NA | NA | Done |  |  |  | Anydesk with Pransshu's account in workspace
2026-05-15 |  | Deloitte and Accenture | Hemanth | VPN | Pransshu |  | Connected to hpe network rdp to 10.30.193.7 and then rdp to 8.40.155.92 | For JS 10.30.193.7: User: Ayushi Password: HrF2JY1RF09k For JS 8.40.155.92 User: Ayushi Password: Password!234 |  | Done |  |  |  | 1st pipeline done with wheels in airgapped network, 4th pipeline done without openai, common cloud in pransshu's account and rdp in hpe network for pcai
2026-05-14 |  | OC Public Defender | Aarti | Screen Share | Sanjana | DJ | NA | NA | NA | Done |  | 1.5 | 1.5
2026-05-15 |  | Ozdilek | Patrik | VPN | Pransshu |  | Global Protect Address: 195.175.54.246:43443 | user name pransshu.g Password: vd#,jK4(6k@1 |  | Done |  |  |  | VPN has MFA. 1st pipline done in airgapped
2026-05-19 |  | DJBC - DC | Shobhna | VPN | Suraj | DJ | vendor.password.co.id | support03 | 3Jx0*8Fr-gzb03 | Done |  | 1 |  | 1st Pipeline done with Airgapped Notebook as it couldnt download from Keras, 4th Pipeline done using openai.
2026-05-19 |  | Ozdilek - retesting | Patrik | VPN | Sanjana |  | Global Protect Address: 195.175.54.246:43443 | user name pransshu.g Password: vd#,jK4(6k@1 |  | Done |  | 1 | 1.5 | VPN has MFA. 1st pipline done in airgapped
2026-05-20 |  | TMH VENTURES | Aarti | Screen Share | Sanjana | DJ | NA | NA | NA | Done |  | 1 | 1
2025-05-26 |  | ISU Deployment (Kocaeli Su ve Kanalizasyon İdaresi Genel Müdürlüğü) | Debaroon | VPN | Pransshu |  | Cisco Secure Client 88.255.175.139:48443 https://hpe-my.sharepoint.com/:b:/p/pransshu_g-ext/IQC5aPObYdK4TJZKe7-ZEFC7ATVyHE-ZnfS6SzhQRXasfj0?e=qwgKHx | pransshu | 8hl-5s?EylwR | Done |  | 2 | 1 | ISU workspace in Pradyut's greenlake account.
2026-05-20 |  | Ashburn | Patrik | VPN | Sanjana |  | 147.123.195.3:23389 | onsiteteam | d20hbWUBQ0GujYtf | Done |  | 1 | 1
2026-05-27 |  | CHEOPS - France | Hemanth | VPN | Suraj | DJ | Forticlient Import | adm-srs@extinfocheops.local | b2VjA%tud3M@kTu | Done |  | 1.5 |  | 4th pipeline done in calling_llm not openai
2026-05-28 |  | MGT | Praveen | VPN | Suraj |  | https://hpe-my.sharepoint.com/:x:/p/suraj_r-s-ext/IQDIN-YIGdZ9RZmGF_e8gQcLAR-IaMvqxWNGHKx2T1GhluM?e=hSoeI4 | suraj.r-s | qdF9CT!B4GgCA3eLYn | Done |  | 1 |  | Unable to Connect to VPN hence used screenshare from Adil (Platform TC) System.
2026-05-29 |  | Dallas Cowboys | Kashif | Screen Share | DJ | DJ | NA | NA | NA | Done
2026-06-03 |  | CVS Health | Kashif | Screen Share | Suraj |  | NA | NA | NA | Done |  | 1 |  | Pipelines executed in customer namespace project-user-corey-threlfall
2026-06-05 |  | NetIP | Nildip | VPN | Sanjana |  | Forticlient Import | hpe_login01 | #S4R3!kFZbBXGQePvrNf | Done |  | 1 | 1.5
2026-06-11 |  | St Jude Children's Research Hospital | Aarti | Screen Share | Sanjana |  | NA |  | NA | Done |  | 2 | 1.5 | Pipelines executed in platform tc namespace project-user-vipin-s
2026-06-10 |  | Datavision | Aarti | Screen Share | Pransshu |  | NA | NA | NA |  |  |  |  | Workspace in customers environment, postgres deployed through kubectl and 4th pipeline executed through requests not openapi. Had an issue with llama deployment resolved it by support. | 5403307045
2026-06-11 |  | QNB Unit 1 | Kashif | Screen Share | Suraj |  | NA | NA | NA | Done |  | 2 |  | Pipelines Executed in customer namespace - Abu Baker Faiz - Due to Security Reasons | 5403343037
2026-06-15 |  | DRI | Kashif | VPN | Sanjana |  | Forticlient - hades.madeira.gov.pt RDP - 10.180.50.1 admin zMLe1C2OPJ7WZyxNxFHe | DIGVIJAYKUMAR | ]@#_x4N#6n.#6#l@jn8y-YK;pxPkVN | Done |  | 5 | 1 | Data Sources werent viewed in the Page. Raised a Support Case on this https://*.ngc.nvidia.com was not whitelisted on the prod network leading to failure in model deployment Pipelines exectuted on Digvijay's account | 5403377920
2026-06-15 |  | MGT 2026 Upgrade | Praveen | VPN | Suraj |  |  |  |  | Done |  | 1 |  | NA | NA
2026-06-16 |  | CTC | Tom Sunder | Screen Share | Sanjana |  | NA | NA | NA | Done |  | 1.5 | 1 | Pipelines executed in customer namespace project-user-sweehan-ang
2026-06-17 |  | QNB Unit 1 Upgrade | Kashif | Screen Share | Suraj |  | NA | NA | NA | Done |  | 1.5 |  | Constant Proxy issues | NA
2026-06-20 | 2026-07-06 | Concat | Debaroon | VPN | Pransshu | Jabali | Wireguard. Conf file. Rdp 10.10.10.1 | [5 empty] | 1 | Deployed llama 8b
2026-06-22 |  | QNB DR Unit | Kashif | Screen Share | Suraj |  | NA | NA | NA | Done |  | 1 |  | NA | NA
2026-06-23 |  | DJBC DC UAT Test | Shobhna | VPN | Suraj |  | Same as DJBC DC |  |  | Done |  | 1 |  | UAT test for DJBC DR Unit
2026-06-23 | 2026-07-13 | Insight Incorporated | Praveen | VPN | Pransshu | Jabali |  |  |  | Done |  | 1.5 | 1 | NA | NA
2026-06-24 | 2026-06-24 | Quantum | Aarti | VPN | Suraj | Jabali | Public Ip: 38.19.41.250 Client : Palo Alto user : pmadhavan Password : k?27t(RS#pm) RDA 172.80.1.100 Administrator Esltda100% |  |  | Done | Done | 1 |  | NA | NA
2026-06-24 |  | GDCC Medium | Shobhna | VPN | Suraj |  | Anydesk ID : 1916648445 Password : HPEadm#2026 Windows Account : HPE Windows Passwork : HPEadm#2026
2026-06-26 |  | GDCC Large | Shobhna | VPN | Suraj |  | Anydesk ID : 1916648445 Password : HPEadm#2026 Windows Account : HPE Windows Passwork : HPEadm#2026
2026-06-26 |  | Tatung Systems Redeployment | Tom Sunder | Screen Share | Pransshu |  | Webex Meeting | NA | NA | Done
2026-06-30 |  | DJBC DR | Shobhna | VPN | Suraj |  |  |  |  | Done |  | 1 |  | NA | NA
2026-07-07 |  | DJBC DR UAT | Shobhna | VPN | Suraj |  |  |  |  | Done |  | 2
2026-07-07 |  | New Media Manitoba | Praveen | VPN | Suraj |  | Wireguard Tunnel provided as Configuration file |  |  | Done |  | 1 |  | Used Automation to perform pipeline testing
2026-07-07 | 2026-07-11 | SLTN | Tom Sunder | Screen Share | Suraj | Jabali | NA | NA | NA | Done |  | 1 |  | Screenshared by customer Gert, Account is mine

## data
Jabali | Done | VPN
DJ | In Progress | Screen Share
Suraj | Blocked
Pransshu | Yet to Start
Sanjana

## Bugs
Date | Customer | PCAI Version | AIE Version | Logs | Solution | Support Ticket
2026-06-14 | QNB | 1.8 | 1.11 | Airflow Not Up due to git sync | Whitelisting in proxy and support team help in bypassing SSL self certification for github url | 5403343037

## Issue_Log
Issue Description | PCAI Version | AIE Version | Solution
Local S3 In error state | Any | Any | Delete and re add using the following commands kubectl get ezdatasources -n ezdata-system local-s3 -o yaml >/tmp/local-s3 kubectl delete ezdatasources -n ezdata-system local-s3 kubectl apply -f /tmp/local-s3
Model issues | Any | Any | kubectl get all -n ezai-services ¦ grep -i llama3-8b kubectl get all -n ezai-services ¦ grep -i reranker kubectl rollout restart deployment reranker-a1db2849-predictor-00001-deployment -n ezai-services kubectl delete configuration.serving.knative.dev/reranker-a1db2849-predictor -n ezai-services
Lllama 3-70b Model Deployment issue | PCAI 1.8 | AIE 1.11 | This is happening with RTX6K GPUs.Where we have to define the NIM_MODEL_PROFILE for the model to get deployed with the correct Profile
Model deployment Failing with error specifying https://xfiles.ngc.nvidia.com | PCAI 1.8 | AIE 1.11 | This mostly is happening because the customer hasnt whitelisted *.ngc.nvidia.com
Model Deployment issue in PCAI-D Environments | PCAI 1.8 | AIE 1.11 | all the required NIM_PROFILEs are not copied into the S3 bucket.the solution for this involves resyncing the NIM_PROFILE buckets and re running
Data Sources Issues | PCAI 1.8 | AIE 1.12 | Restart ezpresto

## Stats
📊 PCAI STATISTICS DASHBOARD
Current Date: | 2026-07-13
📅 LAST 7 DAYS STATISTICS |  |  | 👤 PER RESOURCE OVERALL STATISTICS | [5 empty] | 📅 WEEKLY STATISTICS
Metric | Value |  | Resource | Testing Tasks | Orientation Tasks | Testing Hours | Orientation Hours |  | Week Starting | Testing Tasks | Testing Hours | Orientation Tasks | Orientation Hours
Total Tasks (Testing) | 3 |  | Jabali | 4 | 14 | 14 | 16 |  | 2026-07-13 | 0 | 0 | 1 | 1 | ← Current Week
Total Tasks (Orientation) | 3 |  | DJ | 5 | 21 | 12 | 16.5 |  | 2026-07-06 | 3 | 4 | 2 | 1
Hours Spent (Testing) | 4 |  | Suraj | 27 | 0 | 44 | 0 |  | 2026-06-29 | 1 | 1 | 0 | 0
Hours Spent (Orientation) | 2 |  | Pransshu | 20 | 0 | 3.5 | 0 |  | 2026-06-22 | 7 | 4.5 | 1 | 0
Tasks Completed | 3 |  | Sanjana | 15 | 0 | 44 | 0 |  | 2026-06-15 | 5 | 9 | 0 | 0
Tasks Blocked | 0 |  | Ashish | 3 | 0 | 0 | 0 |  | 2026-06-08 | 3 | 4 | 1 | 2
|  |  | TOTAL | 74 | 35 | 117.5 | 32.5 |  | 2026-06-01 | 5 | 8 | 0 | 0
[9 empty] | 2026-05-25 | 3 | 2.5 | 0 | 0
📈 OVERALL STATISTICS |  |  | 📆 MONTHLY STATISTICS
Metric | Value |  | Month-Year | Testing Tasks | Testing Hours | Orientation Tasks | Orientation Hours |  | 📊 STATUS BREAKDOWN BY RESOURCE
Total Customers | 75 |  | 2025-11-01 | 1 | 6 | 1 | 2 |  | Resource | Done | Blocked | Yet to Start | In Progress
Total Testing Hours | 119.5 |  | 2025-12-01 | 0 | 0 | 0 | 0 |  | Jabali | 4 | 0 | 0 | 0
Total Orientation Hours | 48.5 |  | 2026-01-01 | 0 | 0 | 0 | 0 |  | DJ | 4 | 0 | 0 | 0
Tasks Done | 69 |  | 2026-02-01 | 4 | 5.5 | 0 | 0 |  | Suraj | 25 | 0 | 0 | 0
Tasks Blocked | 0 |  | 2026-03-01 | 8 | 16 | 2 | 3 |  | Pransshu | 17 | 0 | 0 | 0
Tasks Yet to Start | 0 |  | 2026-04-01 | 10 | 29.5 | 4 | 6 |  | Sanjana | 15 | 0 | 0 | 0
VPN Tasks | 38 |  | 2026-05-01 | 15 | 12 | 0 | 0 |  | Ashish | 3 | 0 | 0 | 0
Screen Share Tasks | 30 |  | 2026-06-01 | 21 | 26.5 | 2 | 2 |  | TOTAL | 68 | 0 | 0 | 0
👥 PER RESOURCE PER WEEK STATISTICS (Last 4 Weeks) | [6 empty] | ⏱️ HOURS PER RESOURCE PER WEEK (Last 4 Weeks)
Resource | 2026-07-13 | 2026-07-06 | 2026-06-29 | 2026-06-22 | Total |  | Resource | 2026-07-13 | 2026-07-06 | 2026-06-29 | 2026-06-22 | Total Hrs
Jabali | 0 | 0 | 0 | 0 | 0 |  | Jabali | 0 | 0 | 0 | 0 | 0
DJ | 0 | 0 | 0 | 0 | 0 |  | DJ | 0 | 0 | 0 | 0 | 0
Suraj | 0 | 3 | 1 | 5 | 9 |  | Suraj | 0 | 4 | 1 | 3 | 8
Pransshu | 0 | 0 | 0 | 2 | 2 |  | Pransshu | 0 | 0 | 0 | 1.5 | 1.5
Sanjana | 0 | 0 | 0 | 0 | 0 |  | Sanjana | 0 | 0 | 0 | 0 | 0
Ashish | 0 | 0 | 0 | 0 | 0 |  | Ashish | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 3 | 1 | 7 | 11 |  | TOTAL | 0 | 4 | 1 | 4.5 | 9.5
🔌 TYPE BREAKDOWN BY RESOURCE |  |  |  |  | 📅 CURRENT MONTH STATISTICS
Resource | VPN Tasks | Screen Share Tasks | Total |  | Metric | Value
Jabali | 2 | 1 | 3 |  | Current Month | July 2026
DJ | 0 | 2 | 2 |  | Testing Tasks | 3
Suraj | 18 | 9 | 27 |  | Orientation Tasks | 3
Pransshu | 11 | 9 | 20 |  | Testing Hours | 4
Sanjana | 7 | 8 | 15 |  | Orientation Hours | 2
Ashish | 0 | 0 | 0 |  | Tasks Completed | 3
TOTAL | 38 | 29 | 67
Formulas:
Week Starting = [Week Starting, row above]-7
Testing Tasks = [Resource]-7